## issues
Sr No | Jira ID | Description | Related Tab | Assigned Dev | Dev status | Assign QA | Testing status | Dev completed date | Tetsing completed date | Severity | Priority
1 | LOGBUS-27026 | LOGBUS-27026 - delivery address & saving that Then reloading the data , Same changes are also visible in Invoice Address (Dealer data & user settings) | STOX/Dealer data User settings | Ashish | completed |  | completed | 2022-11-30 | 2022-12-01
2 | LOGBUS-27405 | In dealer data and user setting tab save button functionality not working after editing fields for spain user. https://seu30.gdc-leinf01.t-systems.com/jira/browse/LOGBUS-27405 | STOX-Dealer data User settings | ashish | completed |  | completed | 2022-12-05 | 2022-12-05
3 | LOGBUS-27408 | frist time load data for particular country it get loaded if we want load data for second time for another country it will not load data it shows prevoiusly loaded data https://seu30.gdc-leinf01.t-systems.com/jira/browse/LOGBUS-27408 | STOX-Dealer data User settings | ashish/priyanka | completed |  | completed | 2022-12-05 | 2022-12-05
4 |  | decimal values are not being fetched in t.costs - 3 | STOX-Purchase And Sales Settings | Shital | completed |  | completed | 2022-12-01 | 2022-12-01
5 | LOGBUS-27398 | https://seu30.gdc-leinf01.t-systems.com/jira/browse/LOGBUS-27398 | STOX-Purchase And Sales Settings | Shital | completed | Shubham G | completed | 2022-12-14 | 2022-12-14
6 | LOGBUS-27402 | https://seu30.gdc-leinf01.t-systems.com/jira/browse/LOGBUS-27402 | STOX-Purchase And Sales Settings | Shital | completed |  | completed | 2022-12-02 | 2022-12-05
7 |  | headers in automatic order info fields feels like part of text they need to be given different look or depth | STOX-Purchase And Sales Settings | shital | completed |  | completed | 2022-12-01 | 2022-12-01
8 |  | When we resizing windowthen late pick-up check-box & its field is overlapping | STOX-Purchase And Sales Settings | shital | completed |  | completed | 2022-12-01 | 2022-12-01
9 | LOGBUS-27404 | Minimum value limit per line & Minimum unit price per line field should not get red | STOX-Administration | akash | completed | Shubham G | completed | 2023-01-10 | 2023-01-10
10 |  | when loading data for any country for which data is unavailable then % sign ni deadstock discount rate is not consistent sometimes its not on UI -fixed | STOX-Administration | shital | completed |  | completed
11 | LOGBUS-27403 | Save functionality is showing inconsistency for other than germany data | STOX-Administration | Akash | completed | Shubham G | completed | 2022-12-26 | 2022-12-26
12 | LOGBUS-27662 | Admin Tab: Warning pop up related issue | STOX-Administration | Prasad | completed |  | completed | 2022-12-15 | 2022-12-15
13 | LOGBUS-27387 | Admin: Save/Discard buttons issue | STOX-Administration | prasad | completed |  | completed | 2022-12-13 | 2022-12-13
14 | Logbus-27401 | https://seu30.gdc-leinf01.t-systems.com/jira/browse/LOGBUS-27401 | STOX-Parts scope and discount group matrix | Ashish | completed |  | completed | 2022-12-07 | 2022-12-07
15 | LOGBUS_27565 | Criteria Part Scope: Validation related issues | STOX-Parts scope and discount group matrix | Ashish | completed |  | completed | 2022-12-13 | 2022-12-13
16 | LOGBUS-27666 | Settings - Criteria part scope: validation of cluster fields is not correct | STOX-Parts scope and discount group matrix | Ashish | completed |  | completed | 2022-12-13 | 2022-12-13
17 | Logbus-27517 | Discount Group Matrix: Grid column name is not correct | STOX-Parts scope and discount group matrix | pooja | completed | Shubham G | completed | 2022-12-29 | 2022-12-29 | minor | major
18 | LOGBUS-27399 | Minimum value limit per line & Minimal unit price per line needs to be fixed | Application level | prasad | assigned
19 | LOGBUS-27380 | Loading time issue in STOX App | Application level | piyush | completed | shubham p | completed | 16.03.2023 | 16.03.2023
20 | LOGBUS-27459 | When put dealer number 22600 and select country germany then click on load all data get loaded but in main dealer field toggle switch is at off state which required to an ON state | STOX-Dealer Master data | ashish | completed |  | completed | 2022-12-20 | 2022-12-20
21 | LOGBUS-27536 | When open the application and go to dealer master tab save button observed active in dealer master data tab. initially save button required to be an active state. | STOX-Dealer Master data | priyanka | completed |  | completed | 2022-12-10 | 2022-12-15
22 | LOGBUS-27539 | When we load data in dealer master data tab and click on dealer master data panel then related information for this panel get loaded. But it is difficult to know we are in dealer master data panel. | STOX-Dealer Master data | priyanka | completed |  | completed | 2022-12-16 | 2022-12-19
23 | LOGBUS-27540 | When we load data in dealer master tab at maximize condition it's looks fine but kept at minimize condition all data gets overlap. | STOX-Dealer Master data | priyanka | completed |  | completed | 2022-12-12 | 2022-12-12
24 | LOGBUS-27543 | Dealer number observed in main dealer column fields of sub dealer data table. instead of dealer number Yes/No option is required in that fields. | STOX-Dealer Master data | priyanka | completed |  | completed | 2022-12-16 | 2022-12-19
25 | LOGBUS-27547 | When we see data for sub dealer table its value of main dealer column, DMS column and DMS version columns are not align centered. currently it is left align. | STOX-Dealer Master data | priyanka | completed |  | completed | 2022-12-16 | 2022-12-19
26 | LOGBUS-27550 | In dealer master data panel we can scroll input field's values this input field's required to be stable. | STOX-Dealer Master data | priyanka | completed |  | Discuss with ganesh this raltred with angualr component issue
27 | LOGBUS-27551 | When we load data for dealer number 23300 Copy Dealer and Create Dealer Buttons are inactive. then we load data for dealer number 23670 Copy Dealer and Create Dealer Buttons are active because that dealer doesn't exist yet in the Dealer table, but is already listed in the GSSN table. Again we load data for dealer number 23300 than Copy Dealer and Create Dealer Buttons are active. | STOX-Dealer Master data | priyanka | completed |  | completed | 2022-12-12 | 2022-12-12
28 | LOGBUS-27563 | When load data in Discount rate matrix panel column value get fetch without percentage symbol. | STOX-Parts Scope And Discount Group Matrix | Pooja | completed | Shubham G | completed | 2022-12-26 | 2022-12-27
29 | LOGBUS-27564 | When we load data for particular country in discount rate matrix panel data gets loaded. but data gets loaded without decimal value. | STOX-Parts Scope And Discount Group Matrix | Pooja | completed | Shubham G | completed | 2022-12-26 | 2022-12-27
30 | LOGBUS-27566 | In Discount rate matrix panel when we load data for particularly country data get loaded but country names are not visible in country column fields. instead of country names country code are visible. | STOX-Parts Scope And Discount Group Matrix | Pooja | completed | Shubham G | completed | 2022-12-26 | 2022-12-27
31 | LOGBUS-27570 | When load data in discount rate matrix panel for spain country data get loaded. but only up to 28 rows data get fetch remaining not showing. Also Discount rate VOR columns fields values not fetch. | STOX-Parts Scope And Discount Group Matrix | Pooja | completed |  | completed | 2022-12-13 | 2022-12-15 | Discount rate VOR columns fields values cover underLOGBUS-27564
32 | LOGBUS-27571 | when load data from india country their is not data from that country. no data reuired to show but it shows previously loaded country data. that means previously loaded country data not goan. | STOX-Parts Scope And Discount Group Matrix | Pooja | completed | shubham | completed | 2022-12-13 | 2022-12-14
33 | LOGBUS-27572 | When load specific country in discount rate matrix panel then close application again open the application and see in country combo box field where we can't see previously loaded country name. | STOX-Parts Scope And Discount Group Matrix | Ashish | completed | shubham | completed | 2022-12-22 | 2022-12-22
34 | LOGBUS-27670 | Error popup comes when we put the values equal to central settings of administration tab in the input fields of Deadstock min. value limit & min unit price panel. | STOX-Parts Scope And Discount Group Matrix | Ashish | completed |  | completed | 2022-12-14 | 2022-12-14
35 | LOGBUS-27701 | When we make changes in Discount rates matrix panel and discard that changes by click on yes button of discard pop up at that time it takes time to discard changes | STOX-Parts Scope And Discount Group Matrix | Pooja | assigned
36 | LOGBUS-27710 | Location-based handling margin: Input Field Issue | STOX-Parts Scope And Discount Group Matrix | prasad | completed | shubham | completed | 2022-12-23 | 2022-12-23
37 | LOGBUS-27711 | Location-based handling margin: Net order value per RNR issue | STOX-Parts Scope And Discount Group Matrix | poonam | Completed | shubham G | completed | 2023-01-04 | 2023-01-04
38 | LOGBUS-27712 | Location-based handling margin: Error pop Up is not coming | STOX-Parts Scope And Discount Group Matrix | prasad | completed | shubham | completed | 2022-12-21 | 2022-12-21
39 | LOGBUS-27714 | Settings - Criteria part scope: Discard button disable issue | STOX-Parts Scope And Discount Group Matrix | akash | completed |  | completed | 2022-12-16 | 2022-12-16
40 | LOGBUS-27738 | In D2D Handling margin panel when put the value greater than Max. value feild in the Min. value field and click on save button error pup comes but it also save that values. as per requirement that values should no get saved | STOX-Parts Scope And Discount Group Matrix | shital | completed | Shubham G | completed | 2023-01-02 | 2023-01-02
41 | LOGBUS-27744 | discount rate matrix panel column input fields accept special character and character but as per requirement user should not be able to put value in this fields. | STOX-Parts Scope And Discount Group Matrix | pooja | completed | Shubham G | completed | 2022-12-29 | 2022-12-29 | Major | Major
42 | LOGBUS-27745 | discount rate matrix panel column fields accept numeric digit more than 2 digit but this field required to accept numeric digit max 2 up to digit. | STOX-Parts Scope And Discount Group Matrix | Pooja | completed | Shubham G | completed | 2023-01-05 | 2023-01-05
43 | LOGBUS-27746 | Discount rate matrix panel column fields accept more than two decimals after digit but this field required to accept decimal values after digit up to 2 digit. | STOX-Parts Scope And Discount Group Matrix | Pooja | completed | shubham G | completed | 2023-01-03 | 2023-01-03
44 | LOGBUS-27757 | when we make changes in STOX Parts Scope And Discount Group Matrix tab and click on save changes get save. after that click on reset button data get reset from central setting but when we click on load button previously save data comes. | STOX-Parts Scope And Discount Group Matrix | Akash | completed | Shubham G | completed | 2022-12-29 | 2022-12-29 | Major | Major
45 | LOGBUS-27776 | Location-based handling margin: values are getting converted in infinite sign inconsistently | STOX-Parts Scope And Discount Group Matrix | Rushikesh | completed | Shubham G | completed | 2023-01-05 | 2023-01-05
46 | LOGBUS-27779 | Location-based handling margin: Error popup for empty fields is not coming | STOX-Parts Scope And Discount Group Matrix | akash | completed | Shubham G | completed | 2023-01-03 | 2023-01-03
47 | LOGBUS-27787 | STOX - Settings - Buy and sell: pop up component needs to be changed | STOX-Purchase And Sales Settings | Priyanka | completed | Shubham G | completed | 2022-12-29 | 2022-12-29 | Minor | Major
48 | LOGBUS-27788 | STOX - Settings - Buy and sell: save function: pop up component needs to be changed | STOX-Purchase And Sales Settings | Priyanka | completed | Shubham G | completed | 2022-12-29 | 2022-12-29 | Minor | Major
49 | LOGBUS-27894 | When we put wrong dealer number in Dealer Default input field and click on create button at that time it shows message dealer copy successfully. but actually 'dealer does not exists message' required. | Dealer Master Data/Copy Dealer | poonam | assigned
50 | LOGBUS-27921 | When we put date on In RIMS Active From field at that it also accept character and special character. In RIMS Active From field accept numeric digit more than 8. | Dealer Master Data/Copy Dealer/Create | ashish | completed | shubham p | completed | 2023-01-10 | 2023-01-10
51 | LOGBUS-27922 | When we put manually and select date from calendar in In RIMS Active From field at that time date is not DD/MM/YYYY format | Dealer Master Data/Copy Dealer/Create | ashish | completed | shubham p | completed | 2023-01-10 | 2023-01-10
52 | LOGBUS-27923 | When we filled all input fields of Copy Dealer Dialog Box after click on copy button dealer is copied but Copy Dealer Dialog Box need to be closed. also copy dealer and create buttons should be disabled. currently this dialog box is opened. | Dealer Master Data/Copy Dealer | ashish | completed | shubham p | completed | 2023-01-10 | 2023-01-10
53 | LOGBUS-27924 | When we filled all input fields of Create Dealer Dialog Box after click on create button dealer is created but Create Dealer Dialog Box need to be closed. also copy dealer and create buttons should be disabled. currently this dialog box is opened. | Dealer Master Data/Create Dealer | ashish | completed | shubham p | completed | 2023-01-10 | 2023-01-10
54 | LOGBUS-27963 | Stox: Some integer restricted fields are accepting "+" sign | Application level | ashish | assigned
55 | LOGBUS-27992 | In RIMS Active From input field when we select date from calender and click on Copy Dealer Button Dealer will copied but when we manually put date on that field after click on Copy Button Dealer will not Copied because Copy Button functionality Not work | Dealer Master Data/Copy Dealer | ashish | completed | shubham p | completed | 2023-01-16 | 2023-01-16
56 | LOGBUS-27993 | In RIMS Active From input field when we select date from calender and click on Create Dealer Button Dealer will created but when we manually put date on that field after click on Create Button Dealer will not created because Create Button functionality Not work | Dealer Master Data/Copy Dealer | ashish | completed | shubham p | completed | 2023-01-16 | 2023-01-16
57 | LOGBUS-28056 | Create Dealer button is observed activated state when we either not make Dealer toggle Switch is ON state or Not filled any value in Main Dealer input Field. | Dealer Master Data/Copy Dealer | ashish | completed | shubham p | completed | 2023-01-18 | 2023-01-18
58
59
60
61
62

## Angular Issue
Sr No | Tab | Sub Panel | User Story | Defect ID | Defect Description | Sprint | Comment | Date
1 | STOX-Dealer Master Data | Dealer Master Data | LOGBUS-27019 | LOGBUS-27550 |  | LogBus@Cars Sprint 5 | Mark this defect as invalid because of angular components issue for that discuss with ganesh and priyanka | 2022-12-16
2 | STOX-Parts Scope And Discount Group Matrix | Discount rate matrix | LOGBUS-27482 |  | In Rg matrix panel we follow pagination approach for dividing loaded data. when we go topage number 2-3 and edit something then click on save button. again load data it will load data from page 2-3 not from starting. (Completed: Discuss with ganesh and he said me its new functionality that,s ok) | LogBus@Cars Sprint 5 | Discussion with ganesh he said that’s the new agular functionality that’s ok.
3 | STOX-Parts Scope And Discount Group Matrix | DeadStock cluster definition and exclusion criteria | LOGBUS-26887 |  | When we click on reset button warning pop up is come with "continue" and "cancel" buttons. instead of "continue"/"cancel" buttons "yes"/"No" as per the user story. | LogBus@Cars Sprint 6 | (Dicuss with developer they said this new design that's ok go with working functionlity) | 2022-12-22
4 | Dealer Master Data | Create Dealer | LOGBUS-27015/LOGBUS-27018 | LOGBUS-27922 | When we put manually and select date from calendar in In RIMS Active From field at that time date is not DD/MM/YYYY format | LogBus@Cars Sprint 6 | When we put date manually on Stock from input fields it is not in format like DD/MM/YY :- Input field accepting date in random format like 10012023 but when we click on another field at that time it automatically convert it into DD/MM/YYYY as same like Modernization CORS application. discuss with * More, Ganesh Popat * | 2023-01-10
5 | purchase & sales | purachse sales |  |  | one for multiple same service providers is required
6 |  |  |  |  | if something is selected on right then it should not move from left to right in progress
7 | Dealer Master Data | Create Dealer GSSN | LOGBUS-27018 |  | As per user story country combo box field is not required in Create Dealer dialog box but currently it is present. | LogBus@Cars Sprint 7 | Mahadar, Ashish has discussion with Gaipeli, Pavel, as per pavel suggestion that is new functionality added in Create new Dealer dialog box so user can select other country for creating new dealer.
8 | Dealer Master Data | Create Dealer GSSN | LOGBUS-27018 |  | For Dealer type dropdown field one observation is noted that is as per the Gaipeli, Pavel comment on user story required toggle switch instead of dropdown menu. | LogBus@Cars Sprint 7 | As Mahadar, Ashish said that he had discussion with Gaipeli, Pavel regarding Dealer Type dropdown filed is fine to used.
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32

## Observation
Area | Sub Panel | Sprint | User Story | Observation
STOX-scope and discount group matrix | Discount rate matrix | LogBus@Cars Sprint 5 | LOGBUS-26888 | 1)All country lists are visible in country combo box but when sort country by alphabets country get selected but not coming in view.
|  |  | LOGBUS-26913 | 1) Percentage symbol not coming discount rate matrix column's fields. (LOGBUS-27563) 2) Decimal digit not shown in field's of discount rate matrix column's.(LOGBUS-27564) 3) In country column fields of discount rate matrix panel coutry name not getting. instead of country name their country code is visible.(LOGBUS-27566) 4) country column values of discount rate matrix panel reuired centered align currently it is right align. 5)Discount code column value of discount rate matrix panel required left align currently it is right align. 6) For spain country all data not loaded only 28 rows data get fetch and For spain country values of Discount rate VOR values not getting. (LOGBUS-27570:- completed 15.12.2022) 7) when load data from india country their is not data from that country. no data reuired to show but it shows previously loaded country data. that means previously loaded country data not goan. (LOGBUS-27571:- completed 14.12.2022) 8) Apart from germeny and spain when click load button it takes times to laod data. (LOGBUS-27380) 9)When load specific country and close the appliaction. again open application in discount rate matrix panel perviously loaded country not showing. (LOGBUS-27572:- compeletd 22.12.2022) 10)Discount code column value required in form 00,01,02 but currently it is in 1,2,3. when comapre with old application. 11) Discount rate Cars (LAG) column fields are not editable by logbusall user its only editable by Admin user. but its currently editable by logbusall user. 12) discount rate matrix panel column fields accept numeric digit more than 2 digit but this field required to accept numeric digit max 2 digit.(LOGBUS-27745) 13)Discount rate matrix panel column fields accept more than two decimals after digit but this field required to accept decimal values after digit upto 2 didgit.(LOGBUS-27746) 14)discount rate matrix panel column fields accept special character and character but this field do not accepet special character and character.(LOGBUS-27744)
| D2D Handling margin |  | LOGBUS-26883 | 1) In Minimum value limit per line and Minimal unit price per line fields when we enter value more than central setting error popup not getting(completed:- 15.12.2022) 2) error popup comes when we put the values equal to the minimum and maximum central setting as per adminstration tab. reuirement is that no popup comes when values are equal.(LOGBUS-27670:- completed 14.12.2022) 3) Apart from germany country centerlized setting of adminsatration tab not reflecting in DeadStock min. value limit & min unit price panel. for other countries also germany central settings valadtion are refelecting.(completed:- 15.12.2022)
| D2D Handling margin |  | LOGBUS-27359 | 1)In Location-based handling margin all fields are accpeting + , _,chars, decimals & special chars as input that should not happen.(LOGBUS-27710:- completed 23.12.2022) 2)In D2D Handling margin panel Net order value per RNR field should be disable. Currently that field is editable.(LOGBUS-27711) 3)In Location-based handling margin panel if min value is greater than max value & save is clicked then error popup required. but currently no error pop up comes. (LOGBUS-27712:- completed 21.12.2022) 4)In D2D Handling margin panel when put the value greater than Max. value feild in the Min. value field and click on save button error pup comes but it also save that values. as per requirement that values should no get saved(LOGBUS-27738)
| Discount rate matrix |  | LOGBUS-27482 | 1)Save button is in active state without editing anything in Discount rates matrix 2) In Rg matrix panel we follow pagination approach for dividing loaded data. when we go to page number 2-3 and edit something then click on save button. again load data it will load data from page 2-3 not from starting. (Completed: Discuss with ganesh and he said me its new functionality that,s ok)
| Discount rate matrix |  | LOGBUS-27484 | 1)Discard button is in active state without editing anything in discount rates matrix panel 2)When we discard changes by click on Yes button of discard pop up at that time it takes time to discard changes.
| DeadStock cluster definition and exclusion criteria | LogBus@Cars Sprint 6 | LOGBUS-26887 | 1)when we make changes in STOX Parts Scope And Discount Group Matrix tab and click on save changes get save. after that click on reset button data get reset from central setting but when we click on load button previously save data comes.(LOGBUS-27757) 2)When we click on reset button warning pop up is come with "continue" and "cancel" buttons. instead of "continue"/"cancel" buttons "yes"/"No" as per the user story. (Dicuss with developer they said this new design that's ok go with working functionlity)
STOX-Dealer Master Data | Dealer Master Data | LogBus@Cars Sprint 5 | LOGBUS-27019 | 1) In our application last updated at field are visible under dealer master data panel but as per user story this field is required at upper dealer field 2) when go to dealer master data tab their is dealer name is visible but in old application this dealer name is not visible 3) save button is required to inactive but currently this active. (LOGBUS-27536:- completed) 4) When we select dealer master data panel it shows their realted field but unable to know we are on dealer master data panel(LOGBUS-27539:- completed 19.12.2022) 5) When we resize the browser at minimun condition overlap issue occure (LOGBUS-27540:- compelted ) 6) When put dealer number 22600 and select country germany then click on load all data get loaded but in main dealer field toggle switch is at off state which required to an ON state(LOGBUS-27459) 7) for dealer number 22600 subdealer data not getting in proper order(Complted: 03.01.2023) 8) In sub dealer table section dealer number observed on main dealer column field's but required is with yes/no option(LOGBUS-27543:- compltetd 19.12.2022) 9) In sub dealer table section the values of main dealer column, DMS column and DMS version columns are not centered align that required to centered align (LOGBUS-27547:- completed 19.12.2022) 10) In dealer master data panel we can scroll input field's values this input field's required to be stable.(LOGBUS-27550:- Mark as invalid this issue beacuse of angular components issue discuss with ganesh for that 16.12.2022) 11) when we load data for main dealer 22600 and also sub dealer data get loaded. when we select its sub delaer main dealer toggle switch feild is on ON state but actually to an off state. 12) Copy dealer and create dealer buttons need to be inactive state If the dealer does exist both in the Dealer and GSSN tables. but actually both buttons observed in active state. (LOGBUS-27551:- compelted 12.12.2022)
|  | LogBus@Cars Sprint 6 | LOGBUS-27015 | 1)When load dealer number other than 23300 in Dealer Master Data tab and close application. again open the application it shows only 23300 dealer number not showing other dealer number.(completed: 04.01.2022) 2)In RIMS Active From field automatically current date not coming but in old application it automatically take current date.(Completed: 04.01.2023) 3)In Stock from fields any one radio button not initailly selected but in old application it is inintailly selected.(Completed: 04.01.2023) 4)When we put date manually on Stock from input feilds it is not in format like dd/mm/yyyy (LOGBUS-27922 :- Completed 10.01.2023)(For 3 observation i.e., When we put date manually on Stock from input fields it is not in format like DD/MM/YY :- Input field accepting date in random format like 10012023 but when we click on another field at that time it automatically convert it into DD/MM/YYYY as same like Modernization CORS application.) 5)also accept more than 8 digit.(LOGBUS-27921:- Completed 10.01.2023) 6)Red line occure on input fields of Create Dealer Dialog Box. 7) Aligment not proper in create dealer dialog box.(Completed: 04.01.2023) 8) Supplier Parameters drop drown values not coming in squence like old application. 9) Dealer Types drop down names not coming in squence like old application. (Completed: 04.01.2023) 10)Stock From input fields accept character and special charcter. (LOGBUS-27921:- Completed 10.01.2023) 11)after click on Create Dealer button "Create Dealer Dialog Box" need to be closed.also Copy Dealer and Create buttons need to inactive.(LOGBUS-27924:- Completed 10.01.2023) 12)In RIMS Active From input field accepting + sign 13)In RIMS Active From input field when we select date from calender and click on Create Dealer Button Dealer will created but when we manually put date on that field after click on Create Button Delaer will not created because Create Button functionality Not work (LOGBUS-27993:- Completed 16.01.2023)
| Dealer Master Data /CopyDearler | LogBus@Cars Sprint 6 | LOGBUS-27018 | 1)Red line occure on editing input fields of Copy Dealer Dialog Box. 2)Search and Cancel Buttons background colour become red. 3)In RIMS Active From field automatically current date not coming but in old application it automatically take current date.(Completed: 04.01.2023) 4)When we put date manually on Stock from input feilds it is not in format like dd/mm/yyyy (LOGBUS-27922 :- Completed 10.01.2023)(For 3 observation i.e., When we put date manually on Stock from input fields it is not in format like DD/MM/YY :- Input field accepting date in random format like 10012023 but when we click on another field at that time it automatically convert it into DD/MM/YYYY as same like Modernization CORS application.) 5)Stock From input fields accept numeric digit more than 8digit. (LOGBUS-27921:- Completed 10.01.2023) 6)Stock From input fields accept character and special charcter. (LOGBUS-27921:- Completed 10.01.2023) 7)When we put dealer number in Dealer default input field then click on search button it does not search dealer and also copy dealer dialog box get closed. 8)Aligment not proper in Copy dealer dialog box. 9)When we put wrong dealer number in Dealer Default input field and click on create button at that time it shows message dealer copy successfully. but actually 'dealer does not exsist message' required.(LOGBUS-27894) 10)if valid dealer copied After click on copy dealer button "Copy Dealer Dialog Box" need to be closed.also Copy Dealer and Create buttons need to inactive. (LOGBUS-27923:- Completed 10.01.2023) 11)In RIMS Active From input field accepting + sign 12))In RIMS Active From input field when we select date from calender and click on Copy Dealer Button Dealer will copied but when we manually put date on that field after click on Copy Button Delaer will not Copied because Copy Button functionality Not work (LOGBUS-27993:- Completed 16.01.2023)
STOX-Dealer Master Data | Dealer Master Data /Crate Dearler in GSSN | LogBus@Cars Sprint 6 | LOGBUS-27017 | 1)As per user story warning popup text reuired "This dealer is not in GSSN pool yet. Do you want to add this dealer in GSSN pool?" but actually observed "Do you want to create new dealer".(Completed: 16.01.2023) 2)In Create Dealer dialog box their is two buttons i.e, Create and Cancel. Create Button is required frist and Cancel Button is after. but acutally Cancel button is in frist. (Completed: 16.01.2023) 3)Dealer text input field accpet numeric digit upto nine but currently it is accept only nine digit. 4)Dealer text input field accept special character and character. also accept + and - signs.but Dealer text input reuired to accept only numeric value.(Completed: 16.01.2023) 5)Dealer text input field accept decimal value.but Dealer text input reuired to accept only numeric value.(Completed: 16.01.2023) 6)As per user story country combo box field is not required in Create Dealer dialog box but currently it is present.(Mahadar, Ashish has discussion with Gaipeli, Pavel, as per pavel suggestion that is new functionality added in Create new Dealer dialog box so user can select other country for creating new dealer. ) 7)Postal Code text input field accept special character and character.also accept + and - signs but Postal Code text input reuired to accept only numeric value.(Completed: 16.01.2023) 8)Postal Code text input field does not accept decimal value. but Postal Code text input reuired to accept only numeric value.(Completed: 16.01.2023) 9)Telephone text input field accept special character and character also accept + and - signs but Telephone text inputt reuired to accept only numeric value. (Completed: 16.01.2023) 10)Telephone text input field accept decimal value. but Telephone text input feild reuired to accept only numeric value. (Completed: 16.01.2023) 11)Fax text input field accept special character and character also accept + and - signs but Fax text input field reuired to accept only numeric value.(Completed: 16.01.2023) 12)Fax text input field accept decimal value. but Fax text input field reuired to accept only numeric value. (Completed: 16.01.2023) 13)Main Dealer input field accept special character and character also accept + and - signs but Main Dealer input field reuired to accept only numeric value.(Completed: 16.01.2023) 14)Main Dealer input field accept decimal value. but Main Dealer input field reuired to accept only numeric value.(Completed: 16.01.2023) 15)Create Dealer button is observed activated state when we either not make Dealer toggle Switch is ON state or Not filled any value in Main Dealer input Feild. (LOGBUS-28056 Compelted 18.01.2023) 16)In Create Dealer dialog box alignment not proper between fields and its value 17)For Dealer type dropdown field one observation is noted that is as per the Gaipeli, Pavel comment on user story required toggle switch instead of dropdown menu.(As Mahadar, Ashish said that he had discussion with Gaipeli, Pavel regarding Dealer Type dropdown filed is fine to used.) 18)In Main Dealer input field of Create New Dealer Dialog box when we put dealer number without country code at that time it will not created new dealer show error popup i.e., Main Dealer does not exist.
STOX-Dealer Master Data | Dealer Master Data /Search Dealer | LogBus@Cars Sprint 7 | LOGBUS-27014 | 1)In old appliavtion When we change country code manually and press enter key nothing will happened but in our apllication after pressing enter it will shows spinner. (Completed: 24.01.2023) 2)When we click on search button it takes time to laod data. 3)In old application after click on search button we can see country already present in country combo box then driectly click on search button realted search appear in table but in our application this will not happened when we click on check box after that results appear. (Completed: 24.01.2023) 4)Search results table coloumns value are not align as per old application. Dealer coloum values required left align, city coloumns value required left align, Postal Code coloum values required, Telephone coloumn values required left align. (Completed: 24.01.2023) 5)In old application when we click on check box of telephone field at that time search button is deactivated and it will activated when we put digit above 03. but in our appilication search button is activate even if when put digit less than three.(Completed: 24.01.2023) 6) As per user story Telephone field required to accept "+", "-", and "/" sign. but currently it is not accept.(Completed: 24.01.2023) 7)When sort column of search result table then make changes and then click on search button after search will be appear with sorting. 8)when we put wrong information for search creteria and click on search button it will shows contiously loading not beihave like old application.(Completed: 24.01.2023) 9)Old application search criteria result and Our application search criteria result did'nt match.
STOX-Dealer Master Data | Dealer Master Data /Upload Dealer | LogBus@Cars Sprint 9 | LOGBUS-28200 | 1)No error popup shows when put decimal value in dealer number column fields of excel file sheet 1 and it shows API error 504. but in old application it shows error.(13.03.2023) 2)When put already created dealer number in dealer number column fields of excel file sheet 1 at that time it shows error but error message is not correct. reuired only to shows "Sheet 1: Dealer Number has already been created. Row: 1" but acutal it shows "Sheet 1: Dealer Number is empty, invalid, too short or too long. Row: 1, Sheet 1: Dealer Number has already been created. Row: 1"(09.03.2023) 3)When we kept DIMS active columns field of excel file sheet1 as empty and click on upload button at that time it shows API error. but as per requirment it allowed for upload and also kept Dealer inactive state.(09.03.2023) 4)When we kept Parts group columns field of excel file sheet 2 as empty and click on upload button at that time it shows API error. . but as requirment it shows error message i.e., "Sheet 2: Parts Group is empty or invalid. Row: 1"(09.03.2023) 5)Customer Number columns field of excel file sheet 2 accepting decimal value but it required does not accept decimal value(13.03.2023) 6)In upload dealer it allowed to upload incorrect format of excel file in Dealer Master Data Tab but actually it does not allowed for incorrect format file.
STOX-scope and discount group matrix | STOX-scope and discount group matrix | 6 | LOGBUS-27787

## poitns
NOTES
epsillon sign in d2d is showing only less than 8 digits are provided
Deselection of radio buttons is not working (this is an observation so ticket is not created, confirm with german team once)
Popup used need from Xentry theme - As Priyanka we are using shared componenet so once they use/change to the Xentry theme .so change needed from Application side (This is not a functional bug so no ticket creation)
Minimum value limit per line & Minimal unit price per line values should give error pop up according to the value presnt in admin tab in these fields - US 26878(will get cover under story)
Cluster3 values should be greater than cluster 2 if not pop up comes and vise versa -- US 26878 (will get cover under story)
front end(ng store) - Priyanka (not a functional issue so bug not created)
For spain 0192 D2D handle margin is not showing in old app but in our app it is showing-related to UAM so no bug creation for now
As per LBPS D2D list the dealer margin should be shown or hidden(try with different users)-related to UAM so no bug for now
one save functionality we should do backend validation -(not a functional issue so bug not created)
Dealer Master Data