## Sprint 1
Jira story no. | sub-module | Feature/module | Story description | Story points | Priority
LOGBUS-26008 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-226
LOGBUS-26009 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-227 | 5
LOGBUS-26010 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-228 | 8 |  | st pt. | count | Total | in hours
LOGBUS-26011 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-229 | 5 |  | 5 | 8 | 40 | 640
LOGBUS-26012 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-230 | 8 |  | 8 | 5 | 40 | 960
LOGBUS-26013 | Operating data and user settings | Operation selection | STOX - Settings - Operation selection: Requirement: FKT-GUI-231 | 3 |  | 3 | 1 | 3 | 24
LOGBUS-26014 | Operating data and user settings | Operation selection | STOX - Settings - Operation selection: Requirement: FKT-GUI-232 | [5 empty] | 1624
LOGBUS-26015 | Operating data and user settings | Operation selection | STOX - Settings - Operation selection: Requirement: FKT-GUI-233
LOGBUS-26016 | Operating data and user settings | Operation selection | STOX - Settings - Operation selection: Requirement: FKT-GUI-234
LOGBUS-26017 | Operating data and user settings | Field Description | STOX - Settings - Field description: Requirement: FKT-GUI-235 | 8
LOGBUS-26023 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-236 | 5
LOGBUS-26024 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-237 | 8 |  | 5 | 5 | 25 | 400
LOGBUS-26029 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-316 | 5 |  | 8 | 2 | 16 | 384
LOGBUS-26030 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-418 | 5 |  | 3 | 1 | 3 | 24
LOGBUS-26031 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-238 | 5 |  |  |  |  | 808
LOGBUS-26032 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-239 | 8
LOGBUS-26033 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-240 | 5
LOGBUS-26034 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-241 | 5

## Sprint 2
| Estimated efforts | Story points
Sprint 1 carry over |  |  | Comments
LOGBUS-26009 | 2 days (14h) 3rd Oct - Dev and Unit testing - 4h Testing - 3h | 3 | 4th oct - Localization pending - in progress (4h) Testing not yet started 5th oct - Localization completed |  |  |  | Estimated | Actual
LOGBUS-26010 | 3 days (~ 20h) 3rd Oct - Dev and Unit testing - Completed Testing & code review - 1d | 8 | 4th oct - code review comments Prasad is working (3h) Testing not yet started |  |  | SP1 | 44 | 36
LOGBUS-26011 | 2 days (14h) 3rd Oct - Dev and Unit testing - 3h Testing - 3h | 3 | 4th oct - Unit testing pending (3h) Testing not yet started |  |  | SP2 | 60 | 60
LOGBUS-26012 | 3.5 days (~ 24-25h) 3rd Oct - Dev and Unit testing - 5hrs Testing - 5 hrs | 5 |  |  |  |  | 104
LOGBUS-26013 | 2 days(10h) 3rd Oct - Dev and Unit testing - 6hrs Testing - 3-4hrs | 2
LOGBUS-26023 | 3 days 3rd Oct - Dev and Unit testing - 8hrs Testing - 2-3 hrs | 5
LOGBUS-26029 | 3 days 3rd Oct - Dev and Unit testing - 8hrs Testing - 2-3 hrs | 5
LOGBUS-26030 | 3 days 3rd Oct - Dev and Unit testing - 8hrs Testing - 2-3 hrs | 5
New stories (Sprint 2)
Jira story no. | sub-module | Feature/module | Story description | Story points | Comments
LOGBUS-26008 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-226 | 8 | To be picked in SP3
LOGBUS-26014 | Operating data and user settings | Operation selection | STOX - Settings - Operation selection: Requirement: FKT-GUI-232 | 8
LOGBUS-26015 | Operating data and user settings | Operation selection | STOX - Settings - Operation selection: Requirement: FKT-GUI-233 | 13
LOGBUS-26016 | Operating data and user settings | Operation selection | STOX - Settings - Operation selection: Requirement: FKT-GUI-234 | 8
LOGBUS-26017 | Operating data and user settings | Field Description | STOX - Settings - Field description: Requirement: FKT-GUI-235 | 8
LOGBUS-26024 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-237 | 8 | Not closed
LOGBUS-26031 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-238 | 5
LOGBUS-26032 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-239 | 8
LOGBUS-26033 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-240 | 5
LOGBUS-26034 | Operating data and user settings | Field description | STOX - Settings - Field description: Requirement: FKT-GUI-241 | 5 | File path handling pending
Administration
LOGBUS-26484 | Administration |  | STOX - Settings - Administration - Requirement: FKT-GUI-276 | 5
LOGBUS-26485 | Administration |  | STOX - Settings - Administration- Requirement: FKT-GUI-277 | 5
LOGBUS-26486 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-278 | 13
LOGBUS-26487 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-279 | 8
LOGBUS-26488 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-311 | 5 |  | Admin | 62
LOGBUS-26489 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-312 | 5 |  | Operator data carry over | 5
LOGBUS-26490 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-313 | 5 |  | 26008 from operator data | 8
LOGBUS-26491 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-280 | 8 |  | Buy & sell | 52
LOGBUS-26492 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-281 | 8 |  |  | 127
LOGBUS-26493 | Administration |  | STOX - Settings - Administration- Button overview

## Sprint 3
| Estimated efforts | Story points
Sprint 2 carry over |  |  | Comments
LOGBUS-26034 (Operating data and user settings) | 3-4 days | 5 | File path handling - Priyanka 21/10: Not started 28/10 - Need to change the approach and try |  | 21 Pts
Frontend unit tests(Operating data and user settings) | 5 days - 40hrs | 8 | Priyanka
Backend unit tests(Operating data and user settings) | 3 days - 20hrs | 5 | Ashish and Shital 21/10: To be completed by today EOD 24/10: An issue has been identified. Fixing by today eod. 25/10: Completed, commiting code today 26/10 - Code commited
Automated test scripts - Cucumber integration | 5 days - 40hrs | 8 | Both Shubham 21/10: Xcentry unable to Install. To try workaround. 25/10: Workaround not working. Need to park this task aside
Defects |  |  | 21/10: 2 defects pending, 3 defects ready for retest 24/10: 2 defects fixed and retested, 1 needs to reopen 1 defect pending for fix 31/10 - 1 defect pending for retest, 1 pending for fix
Regression testing on Old Stox application | Next week till 3rd Nov |  | Both Shubham and Ganesh Almost completed.. Couple of tests to be checked with Nikita
26
New stories (Sprint 3)
Jira story no. | sub-module | Feature/module | Story description | Story points | Comments
LOGBUS-26008 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-226 | 8
Administration
LOGBUS-26484 | Administration |  | STOX - Settings - Administration - Requirement: FKT-GUI-276 | 5
LOGBUS-26485 | Administration |  | STOX - Settings - Administration- Requirement: FKT-GUI-277 | 5
LOGBUS-26486 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-278 | 13
LOGBUS-26487 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-279 | 8 |  |  |  | Admin tab |  |  |  | Comments
LOGBUS-26488 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-311 | 5 |  | Admin | 62 | Pooja - Prasad, Rushi, Akash, Poonam | Frontend | 90% | 2 days | Refactoring and any gap fill work
LOGBUS-26489 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-312 | 5 |  | Operator data carry over | 5 | Poonam | Backend | Completed | 0 day
LOGBUS-26490 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-313 | 5 |  | 26008 from operator data | 8 | Review and comments |  |  | 0 day | FE review pending and will be part of refactoring
LOGBUS-26491 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-280 | 8 |  | Buy & sell | 52 | Testing
LOGBUS-26492 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-281 | 8 |  |  | 127 | Defect fix
LOGBUS-26493 | Administration |  | STOX - Settings - Administration- Button overview |  |  |  | 26
| Buy and Sell | [5 empty] | 153
LOGBUS-26773 | Buy and Sell |  |  | 3 |  |  | 40
LOGBUS-26776 | Buy and Sell |  |  | 8
LOGBUS-26777 | Buy and Sell |  |  | 2

## Sheet1
26872 | 5
26873 | 5
26874 | 3
26875 | 8
26876 | 2
26877 | 2
26878 | 3
26879 |  | to be checked by Ganesh
26880 | 3
26883 | 5
26884 |  | to be checked by Ganesh
26885 | 3
26886 | 5
26887 | 5

## Sprint 4
| Estimated efforts | Story points
Sprint 3 carry over tasks |  |  | Comments
LOGBUS-26034 (Operating data and user settings) | 3-4 days | 5 | File path handling - Priyanka 21/10: Not started 28/10 - Need to change the approach and try |  | 21 Pts
Frontend unit tests(Operating data and user settings) | 5 days - 40hrs | 8 | Priyanka
Automated test scripts - Cucumber integration | 5 days - 40hrs | 8 | Both Shubham 21/10: Xcentry unable to Install. To try workaround. 25/10: Workaround not working. Need to park this task aside
Sprint 3 carry over Stories
Jira story no. | sub-module | Feature/module | Story description | Story points | Comments
LOGBUS-26008 | Operating data and user settings |  | STOX - Settings - Requirement: FKT-GUI-226 | 8
Administration
LOGBUS-26484 | Administration |  | STOX - Settings - Administration - Requirement: FKT-GUI-276 | 5
LOGBUS-26485 | Administration |  | STOX - Settings - Administration- Requirement: FKT-GUI-277 | 5
LOGBUS-26486 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-278 | 13
LOGBUS-26487 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-279 | 8 |  |  |  | Admin tab |  |  |  | Comments
LOGBUS-26488 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-311 | 5 |  | Admin | 5 | Pooja - Prasad, Rushi, Akash, Poonam | Frontend | 90% | 2 days | Refactoring and any gap fill work
LOGBUS-26489 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-312 | 5 |  | Operator data carry over | 21 | Poonam | Backend | Completed | 0 day
LOGBUS-26490 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-313 | 5 |  | 26008 from operator data | 8 | Review and comments |  |  | 0 day | FE review pending and will be part of refactoring
LOGBUS-26491 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-280 | 8 |  | Buy & sell | 73 | Testing
LOGBUS-26492 | Administration |  | STOX - Settings - Administration:Field description- Requirement: FKT-GUI-281 | 8 |  | Dealer master data |  | Defect fix
LOGBUS-26493 | Administration |  | STOX - Settings - Administration- Button overview
New Sprint 4 stories | [6 empty] | 107
Buy and Sell
LOGBUS-26773 | Buy and Sell |  |  | 3
LOGBUS-26776 | Buy and Sell |  |  | 8
LOGBUS-26777 | Buy and Sell |  |  | 2
LOGBUS-26778 | Buy and Sell |  |  | 13
LOGBUS-26774 | Buy and Sell |  |  | 13
LOGBUS-26775 | Buy and Sell |  |  | 13
LOGBUS-26868 | Buy and Sell |  |  | 3
LOGBUS-26869 | Buy and Sell |  |  | 13
LOGBUS-26870 | Buy and Sell |  |  | 5
73
Dealer Master data

## Sprint 5
| Estimated efforts | Story points | 124 story pts.
Sprint 4 carry over tasks |  |  | Comments |  |  |  |  | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16
LOGBUS-26034 |  | 5 |  | No Solution available for file path set. Ganesh to update the story | Ganesh to chase with Robert | Close post logging worklog | Closed |  |  |  | Invalid
LOGBUS-26776 |  | 8 | AC missing | Need update on this on priority | AC Updated | Shital to add tasks Partially story is completed | Need to discuss with Ganesh |  | will be covered as part of 26778 |  | Carry over
LOGBUS-26778 |  | 13 | 80% dev work pending | 50% to finish | backend code commit by 6th eod, validations to be confirmed by Ganesh | Backend code commited without validations Front end --In progress | BE - today eod code commit FE - Analysing |  | FE - today eod w/o validation BE code committed |  | Carry over
LOGBUS-26775 |  | 13 | backend Testing task | a day to finish | target to complete by 6th eod | Story completed |  |  |  |  | Closed
LOGBUS-26869 |  | 13 |  | Target to finish by 8th | Shital to pick this backend Pooja frontend | Carry over |  |  |  | Backend can be completed FE to be completed n next Sprint | Carry over
LOGBUS-26878 |  | 3 |  | Testing pending - 6 eod | Closed | [5 empty] | Closed
LOGBUS-26879 |  | 5 | Not estimated | Not started | Add AC if not present | Check with Ashish |  | Completed and ready for testing | Testing in progress | UI testing completed, scripting in progress. Completed the functionalitz | Closed
LOGBUS-26880 |  | 3 | Not started. Ganesh to check | Testing pending | Add AC if not present | Testing in progress | Today eod |  | Testing completed, bugs in progress | Closed | Closed
LOGBUS-26883 |  | 5 | Not started. Ganesh to check | Not started | Add AC if not present | Check with Ashish |  | Completed and ready for testing | Testing in progress | 1 defect pending, scripting pending | Closed
LOGBUS-26884 |  | 3 | Not estimated | Not started | Add AC if not present | Check with Ashish |  | Completed and ready for testing | Testing completed, Story closed | Storz needs to be reopened. Dependent on 26887 | Carry over
LOGBUS-26885 |  | 3 | Not started | Can complete | Add AC if not present | Check with Ashish |  | Completed and ready for testing | Testing in progress | Testing tasks not present | Carry over
LOGBUS-26886 |  | 5 | Not started | Can complete | Add AC if not present Ashish started | Dev completed, Shubham to check on testing |  | Code has been committed but need confirmation on cron job details | Testing in progress | UI testing completed, scripting in progress. Completed the functionalitz | Carry over
LOGBUS-26887 |  | 5 | Not started | Can complete | Add AC if not present | Check with Ashish |  |  | Ganesh to check | Akash started | Carry over
LOGBUS-26914 |  | 5 | Not started | Can complete | Add AC if not present | Backend Ganesh working FE Pooja owrking | today eod code commit | Started |  | Pooja to update on this | Carry over
LOGBUS-27482 |  | 8 |  |  |  | Tomorrow commit code | today eod code commit | Completed and ready for testing |  | 1 Defect pending | Carry over
LOGBUS-27484 |  | 3 |  |  |  | Tomorrow commit code | today eod code commit | In progress | Completed , code commit today | Code commit done, testing to pick | Carry over
LOGBUS-27019 (dealer master) |  | 13 | FE pending | Testing in progress - 6 eod | Observations shared with Priyanka | Defects pending | pick the defects to fix by priyanka | still few defects pending |  | 2 defects remaining | Carry over
LOGBUS-26008 |  | 8 | Not started | Can complete |  | Partial completed check with Ashish | Rushikesh started | In progress |  | 2 tabs in progress | Carry over
LOGBUS-26888 |  | 3 | Code commit and testing pending | Testing in progress - 7 eod |  | To be closed today | Closed |  |  |  | Closed
LOGBUS-26889 |  | 8 | Code commit and testing pending | Testing in progress - 7 eod |  | To be closed today | Defects raised |  | Close |  | Closed
LOGBUS-26913 |  | 13 |  | Coding target - 5 eod | 6th code commit | In progres | Defects raised |  |  | defects pending | Carry over
LOGBUS-26323 |  | 13 |  | Ganesh to work on priority | [6 empty] | Carry over
Sprint 5 Stories
Jira story no. | sub-module | Feature/module | Story description | Comments
Location based margin
LOGBUS-27358 | Location based margin |  | STOX - Settings - Location-based handling margin: FKT-GUI-395 | Not started | Ganesh to assign | Not assigned |  |  |  |  | Carry over
LOGBUS-27359 | Location based margin |  | STOX - Settings - Location-based handling margin: FKT-GUI-396 | In progress 5 eod dev target | 6th eod code commit | Facing issues with functionalitz | To commit code today, open for testing | Code commited and ready for testing | Testing in progress | Testing in progress | Carry over
LOGBUS-27015 | Dealer Master data |  | Dealer Master Data - Create a dealer | Assigned to Priyanka |  | started and in progress |  | API integration pending | FE completed BE Ashish started | BE code is in progress | Carry over
New Sprint 4 stories
Buy and Sell
Dealer Master data

## Sprint 6
Sprint 5 carry over tasks | Efforts (in hours) | Total (in hours) | Comments
LOGBUS-26776 and LOGBUS-26778 | Dev - 12 Testing - 9 Total 21 | 21 | 19/12 - Validation in progress, BE and FE analysis required 20/12 - validation one part pending 22/12 - havent worked yet 27/12 - In progress 28/12 - Dev completed, ready for testing 29/12 - 2 defects raised and fixed. Retesting in progress. 2 validation pending due to logbus-26869. 30/12 - 2 defects restesting completed. 2 validation pending due to logbus-26869. scripting pending and will be started on mostly Monday . 03/01 - validations done. Scripting pending, facing some issue with Cypress. 04/01 - Issue not resolved yet. Scripting pending
LOGBUS-26869 | Dev - 32 Testing - 20 Total 52 | 52 | 19/12 - BE completd, FE today to start 20/12 - FE in progress 21/12 - FE in progress (40%) 22/12 - FE in progress 27/12 - 70% FE done. Priyanka to pick rest of it 28/12 - FE In progress 29/12 - Code commit by today eod or tmrw first half 30/12 -Code commit by today eod. 02/01 - to commit the code today 03/01 - cosmetic changes pending, code checked in for rest of the thing. Testing to pick up. 04/01 - Few more fixes identified (7-8). | Ganesh to confirm on the observations | Defects fix time??
LOGBUS-26884 | Dev - 1 Testing - 4 Total 5 | 5 | dependent on 26887 19/12 - check with testing wth latest code 20/12 - pending to check by Shubham 21/12 - UI testing done. Scripting in progress 22/12 - Scripting pending 27/12 - S. Gupta to pick 28/12 - Scripting completed. Check on a observation 29/12 - Story completed
LOGBUS-26885 | Dev - 0 Testing - 2 Total 2 | 2 | defect fix pending 19/12 - Completed, 1 defect pending 20/12 - defect fix pending - Pooja 22/12 - 1 defect pending(LOGBUS-27701 - Ashish assign to someone 27/12 - Pooja to pick 30/12 - Pooja to pick on Monday. 03/01 - started today 04/01 - 27701 performance related defect. push to backlog. Mark story as complete.
LOGBUS-26886 | Dev - 0 Testing - 4 Total 4 | 4 | 19/12 - scripting pending 20/12 - scripting pending 22/12 - scripting pending 27/12 - S. Gupta to pick 29/12 - scripting completed. Story to close
LOGBUS-26887 | Dev - 1 Testing - 4 Total 5 | 5 | 19/12 - localization pending 20/12 - completed localization, ready for testing 22/12 - Testing completed, defect discussed with Akash(raise in Jira) 27/12 - Akash working. 28/12 - defect fixed, code not committed 29/12 - Code commited and assigned for retest 30/12 - testing ,scripting -completed
LOGBUS-26914 | Dev - 6 Testing - 6 Total 12 | 12 | 19/12 - validation pending 20/12 - Pooja to update 21/12 - still in progress 22/12 - Facing issue, discussing with Ashish 27/12 - to pick today 28/12 - today eod to finish 29/12 - validation code commited. Ready for testing 30/12 - defect reopened assinged to Akash LOGBUS-27745,LOGBUS-27746 02/01 - Defects fix still pending 03/01 - 27746 retested & closed, 27745 pending 04/01 - 27745 is in progress | Closed
LOGBUS-27482 | Dev - 8 Testing - 10 Total 18 | 18 | 19/12 - code commit today, ready for testing 20/12 - Testing in progress 22/12 - Testing completed. Pooja to check on one of the issue raised. Issue resolved. 27/12 - S. Gupta to check on this 29/12 - Give final testing check today 30/12 -scripting to be completed by today 02/01 - Story closed | Shubham comment to address by ganesh
LOGBUS-27484 | Dev - 0 Testing - 2 Total 2 | 2 | defect fix pending 19/12 - code fixed for bug, commit code today 20/12 - Pooja to update 21/12 - code commited for defects 22/12 - some issue with pull request. Code checkin still pending 27/12 - LOGBUS-27701 defect pending to fix 30/12 -Pooja to check on the approach Monday 03/01 - started today 04/01 - 27701 performance related defect. push to backlog. Mark story as complete.
LOGBUS-27019 (Select dealer) | Dev - 2 Testing - 2 Total 4 | 4 | 19/12 - 1 defect pending 20/12 - Retest in progress 21/12 - 3 defects to be discussed with shubham 27/12 - Ashish to fix 28/12 - Dev completed. Shubham to check on defect retest and scripting 29/12 - Testing pending 30/12 -To be picked on Monday 02/01 - Testing in progress 03/01 - Testing completed. Some observations need clarification by Ganesh 04/01 - Ashish to pick some code fix | Closed
LOGBUS-26008 | Dev - 4 Testing - 3 Total 7 | 7 | 19/12 - dev part completed 20/12 - coding In progress 21/12 - Unit testing error fixing 22/12 - code commit today, ready for testing 27/12 - re-commit code. 28/12 - 8hours work pending from dev 29/12 - code commited and ready for testing. E2E cannot be tested , new requirement to be created for it 02/01 - to be closed with BE work done.
LOGBUS-26913 | Dev - 0 Testing - 10 Total 10 | 10 | Defects- 4 19/12 - 2 defects pending 20/12 - Pooja to update 21/12 - defects fixed 22/12 - code commit pending 27/12 - S. Gupta check on defect retest. LOGBUS-27746 pending fix 28/12 - 1 defect reopened, code fixed, awaiting code comit 29/12 - defects assigned for retest 30/12 - 2 defects reopened LOGBUS-27745,LOGBUS-27746 02/01 - Ashish to check 03/01 - 27746 completed. 27745 Pooja to work upon 04/01 - 27745 will be covered as part of 26914 requirement. This can be closed.
LOGBUS-26323 | Docker - 30 | 30 | 27/12 - Pull code from bitbucket. Facing issue on Mac 30/12 - GPCOne needs to be added in order to access the code repo . loading data to Postgres in progress today eod to be completed. 02/01 - Postgres in progress and manually uploading the data in progress 03/01 - Postgres almost done. Copy code to be picked up 04/01 - Postgres data loading completed. Copy code in progress 05/01 - | 40 hours more - 5 days
LOGBUS-27358 | Dev - 0 Testing - 0 Total 0 |  | UAM specific push to backlog
LOGBUS-27359 | Dev - 0 Testing - 2 Total 2 | 2 | Defects - 3 19/12 - assign to Prasad 20/12 - 1 defect fixed, 2 in progress, new bug logged 22/12 - 1 defect retested and closed, 2 defects code checkin today 27/12 - Code checkin done. Retest in progress 28/12 - 1 defect reopened, 2 new defects logged and assigned to Siddhant 30/12 - LOGBUS-27779 coding completed( Akash to commit code) -- Retested & closed LOGBUS -27738 completed(Poonam) -- Retested & closed LOGBUS - 27711 Inprogress , complete and commit the code today(Poonam) - -Retested & closed LOGBUS-27776 - Rushi working | Closed
LOGBUS-27015 (Create dealer) | Dev - 20 Testing - 16 Total 36 | 36 | 19/12 - BE completd, FE 50% completed 20/12 - FE code in progress 21/12 - 90% completed 27/12 - FE completed. Ready for testing 28/12 - Testing pending 30/12 - Testing to be started on Monday. 02/01 - Testing in progress 03/01 - Testing completed. Obersations to discuss with Priyanka 04/01 - 8 observations needs to be logged in Jira (Ashish)
210
New Sprint 6 stories |  | Story points
LOGBUS-27014 (Search Dealer) |  | 13 | Cannot accommodate in this sprint
LOGBUS-27018 (Copy dealer) |  | 13 | FE assign to Poonam. 27/12 - today eod dev complete 28/12 - FE completed, API integration pending, BE API ready, integration pending 29/12 - Facing issue on code commit. 30/12 -code commited , Ready for testing Monday testing can be picked . 02/01 - Testing in progress 03/01 - In progress 04/01 - Testing completed. 8 observations found. 1 is critical - poonam working to fix it.
LOGBUS-27017 (Create dealer GSSN) |  | 13 | 22/12 - BE started, FE assigned to Rushikesh 27/12 - FE Ashish to pick BE - Ashish completed 70% code 28/12 - Queries outstanding. Need Pavel 02/01 - Ashish to connect with Pavel today 03/01 - Flag raised. To be discussed with customer by Pavel. 04/01 - Queries pending from Pavel. UI code is prepared, integration of BE and FE pending.
39
LOGBUS- 27738, 27776, 27779, 27711 defects |  |  | Assigned to Siddhant

## Sprint 7
Sprint 6 carry over tasks | Efforts (in hours) | Total (in hours) | Comments
LOGBUS-26776 and LOGBUS-26778 | Scripting - 6 | 6 | 06/01 - Scripting pending. 09/01 - Scripting in progress 10/01 - blocked due to cypress issue 11/01 - No update 12/01 - Solution in progress 13/01 - Scripting completed for 776, 778 is pending(LOGBUS-28008) 16/01 - 778 scripting completed
LOGBUS-28015 |  |  | 17/01 - logged today, Prasad to work 19/05 - pending to pick | Carry over
LOGBUS-26869 | Dev /defects - 16 Testing - 20 | 36 | 06/01 - Total 9 observations. 09/01 - 4 fixed, 1 in progress 4 more observations from dev - 1 fixed, 3 in progress 10/01 - 3 pending for fix(Rushi) out of 9, rest all closed. Scripting in progress 11/01 - Scripting to complete today eod. 1 fix pending. 12/01 - 2-3 observations newly found. Working on it. Scripting to cover these ones. 13/01 - Today to complete fixes. 16/01 - today to complete Scripting to cover is pending. 17/01 - Fixes are done, BE changes also completed. Scripting in progress. 18/01 - Scripting in progress - 1 validation pending 19/01 - Testing in progress. Today to complete everything 20/01 - 3 defects to fix. In progress. 23/01 - 1 issue to be discussed with Priyanka. 24/01 - today to close the issue fix. 25/01 - 1 perf related issue, others are fixed and testing closed. | Close the story
LOGBUS-27019 (Select dealer) | Scripting - 6 | 6 | 06/01 - Scripting pending and one part has UAM dependency. 09/01 - Scripting in progress 10/01 - Scripting in progress 11/01 - Scripting completed (LOGBUS-27967
LOGBUS-26323 | Docker - 40 | 40 | 06/01 - Code copy in progress 09/01 - Copy code completed, setting FE and BE 10/01 - Facing issue to download angular(FE) 11/01 - Xcentry issue. Trying to manually copy from windows to Mac. Dependency on AdminLAN 13/01 - Not much progress on dependencies. 16/01 - Finding dependencies in manual copy. 25/01 - Task closed as Invalid. Moving to DevClient.(LOGBUS-28233 ) Ganesh to update
LOGBUS-27015 (Create dealer) and LOGBUS-27018 (Copy dealer) | Dev/defects - 16 Testing - 16 Total 32 | 32 | 06/01 - 5 Observations to log in Jira and fix 09/01 - 4 observations fixed and committed. Shubham P. to confirm on this 10/01 - retest pending 11/01 - Retest completed. Scripting to be picked. Create new defect for calendar issue 12/01 - 2 defects raised. 13/01 - Today eod to fix those 2 defects. 16/01 - Defects fixed still some observations shared. discussed with Ashish. Scripting in progress 17/01 - all fixes completed and closed. Scripting in Progress 18/01 - Scripting in progress 20/01 - Scripting in progress 23/01 - Scripting in progress | Close the story / open scripting task
LOGBUS-27017 (Create dealer GSSN) | Dev/defects - 16 Testing - 24 Total 40 | 40 | 06/01 - Integration and UI 09/01 - To be picked 10/01 - To be picked 11/01 - BE API completed, integration in progress 12/01 - Integration completed, working on localization. 13/01 - Localization completed. Ready for test. 17/01 - Testing in progress. observations logged 18/01 - Observations closed. 1 pending with Pavel & 1 for alignment. Scripting in progress 19/01 - 70% scripting completed. 20/01 - Scripting completed. Story can be closed.
Defect LOGBUS-27399 | Dev/defects - 8 Testing - 2 | 10 | 09/01 - In progress (Prasad) 10/01 - Fixed, need to commit. 11/01 - Reopened 12/01 - Fix done, code to commit in sometime. 13/01 - Code commited and tested and closed
Defect LOGBUS-27404 | Dev/defects - 8 Testing - 1 | 9 | 09/01 - In progress 10/01 - Fixed and commited. Ready for retest 11/01 - Fixed and retested
Defect LOGBUS-27701 | Dev/defects - 8 Testing - |  | 10/01 - In progress 11/01 - today eod to commit 12/01 - code commit today 13/01 - Defect closed for discount matrix. New defect to log for criteria scope.
Defect LOGBUS-28013 |  |  | 17/01 - Fixed and retested. Closed
Defect LOGBUS-27380 | Dev/defects - 8 Testing - 2 | 10 | 09/01 - Not picked 10/01 - Not picked yet 11/01 - Not picked yet 12/01 - Analysis in progress. 16/01 - Analysis in progress. 25/01 - previous issue resolved.
Defect LOGBUS-28004 |  |  | 13/01 - Fixed, retest pending 16/01 - Retest done and defect closed
189
New Sprint 7 stories |  | Story points
LOGBUS-26396 (Automation task) |  | 5
LOGBUS-26392 (Automation task) |  | 3
LOGBUS-27043 (Upload dealer) client | Dev - Testing - | 5 | 11/01 - assigned to Poonam 12/01 - In progress 13/01 - last part of AC Is pending 16/01 - working on errors 17/01 - working on validations - sheet 1 18/01 - working on validations - sheet 1 25/01 - code commited without validation. UI testing in progress | 5+8
LOGBUS-28200 client validations |  | 8 | 25/01 - Sheet 1 validations - facing issues. Started with sheet 2
LOGBUS-27930 (Upload dealer) server | Dev - Testing - | 8 | 11/01 - assigned to Akash 12/01 - In progress 13/01 - BE in progress 17/01 - BE in progress 18/01 - BE coding completed without validations.. Poonam to pick 25/01 - UI testing not picked yet | 8+5
LOGBUS-28203 server validations |  | 5
LOGBUS-27920 | Dev - 32 Testing - | 8 | 12/01 - Priyanka to pick 13/01 - Pooja to pick. 16/01 - Requirement analysis in progress 17/01 - In progress 18/01 - Coding in progress 20/01 - BE in progress 23/01 - BE completed. FE in progress 24/01 - FE in progress(50% done) 25/01 -
Code cleanup task LOGBUS-27944 |  | 13 | 11/01 - Rushi working. 12/01 - In Progress 25/01 - Activity completed. Few errors are outstanding. Can be marked as closed | Close the task
Create separate application for dealer master
LOGBUS-27014 (Search Dealer) |  | 13 | 11/01 - Shital to start BE, Ashish on FE 12/01 - Analysis on BE in progress. FE not picked 13/01 - Analysis on BE in progress. FE not picked 16/01 - Analysis on BE in progress 17/01 - FE started, BE analysis completed. Started with coding. 18/01 - BE to complete today, FE in progress. 19/01 - APi completed from BE side. FE in progress 20/01 - 90% FE coding completed. 1 more API required. Shital working on it. 23/01 - FE completed, API completed but faced some issue 24/01 - Code commited. Shubham working on UI testing 25/01 - one query for Pavel and 1 perf related defect., 1 for UAM. | Closed
Task LOGBUS-28076 |  |  | 19/01 - In progress - Prasad 20/01 - In progress 23/01 - 2 panels completed, other 2 in progress 24/01 - 2 panels code commited, other 2 panels 70% work completed. Gupta working on testing on 2 panels 25/01 - 2 panel testing done, few issues found, prasad is checking
68
AM Tasks
AdminLAN setup |  |  | EUR pending
Test case execution
Backend setup Old app |  |  | Completed
Frontend setup Old app |  |  | Completed
New app - Backend setup |  |  | In progress
New app - Front end setup |  |  | To pick

## Sprint 8
Sprint 7 carry over tasks | Efforts (in hours) | Total (in hours) | SP original | Actual SP work | Comments
LOGBUS-28015 | Dev - 8 Testing - 7 | 15 | 3 | 3 | 17/01 - logged today, Prasad to work 19/05 - pending to pick 30/01 - Rushi picked 31/01 - In progress 1/02 - code completed, localization in progress 02/02 - Localization completed. Code about to commit. 03/02 - Code commited and testing completed as well. Need to close | by 1st - dev complete & 2nd Feb testing should be done
LOGBUS-28233 | Docker - 36 | 36 | 8 | 8 | 25/01 - Task closed as Invalid. Moving to DevClient.(LOGBUS-28233 ) Ganesh to update 31/01 - Trying the interim approach till we get the license 1/02 - merged the code, Hungary trying to code locally. Facing some errors 02/02 - Hungary facing issue due to adminLAN, we are creating local db on Ashish system. 03/02 - UAM databse is up locally, e2e not working, minor issues to fix. 06/02 - Integration of code to do along with fixing the code related issues 15/02 - Sebastian Göltz created 2 users in keycloak for the local setup. Still awaiting on Docker license. | Close the task with appropriate comments
Defect LOGBUS-27380 | Dev/defects - Testing - |  |  |  | 25/01 - previous issue resolved. Updated the defect with further issues 31/01 - Priyanka to update the current defect with comment for closing the ticket and open new ticket for remaining work 03/02 - trying few more scenarios 06/02 - Few cases need to discuss with Robert 08/02 - Need some expertie on NGXs | Need estimation
LOGBUS-27043 (Upload dealer) client | Scripting - 4 | 4 | 5 | 1 | 25/01 - code commited without validation. UI testing in progress 31/01 - UI testing is completed. Scripting pending 03/02 - today eod to complete 06/02 - Can close
LOGBUS-28200 client validations | Dev - 16 Testing - 20 | 36 | 8 | 5 | 25/01 - Sheet 1 validations - facing issues. Started with sheet 2 31/01 - Sheet 1 validations are completed for FE. Sheet 2 are code completed and unit testing in progress 01/02 - sheet 2 in progress 02/02 - Sheet 2 reading still in progress 03/02 - Sheet 2 in progress 06/02 - 20% coding pending
LOGBUS-27930 (Upload dealer) server | Dev - Testing - 4 | 4 | 8 | 1 | 25/01 - UI testing not picked yet 31/01 - UI testing completed. Scripting pending 06/02 - Can close
LOGBUS-28203 server validations | Dev - 24 Testing - 20 | 44 | 5 | 5 | 31/01 - BE started 01/02 - in progress 06/02 - In Progress 07/02 - In progress 08/02 - working on save button
LOGBUS-27920 | Dev - 4 Testing - 12 | 16 | 8 | 2 | 31/01 - Code completed, peer testing in progress. 01/02 - code review done, code commit in progress 02/02 - code commit pending, faced some issues 03/02 - Bug found this code not commited. 06/02 - Still in progress 07/02 - 3 APIs to be checked, working on defect 08/02 - in progress(defect logbus-28392). 1 day ETA 09/02 - Trying to resolve few issues of null data 10/02 - in progress
Task LOGBUS-28076 | Defects - 16 Testing - 24 | 40 | 5 | 5 | 25/01 - 2 panel testing done, few issues found, prasad is checking 31/01 - working on observations. 01/02 - all observations done except 1 which is in progress 02/02 - observations completed and commited. 03/02 - Post todays demo, code changes will be merged and available for tesitng 06/02 - Need to assign to others for defect fixes 07/02 - Rushi picked, in progress 08/02 - working on few gaps found. 2 days ETA 09/02 - last point in progress 10/02 - Code completed. some Css things pending 13/02 - Code commited, testing in progress 15/02 - COmpleted and closed
LOGBUS-28351 |  |  |  |  | 03/02 - assigned to Rushi 06/02 - code completed, working on validations - need confirmation 07/02 - today eod test scripting to complete 08/02 - In progress 09/02 - Scripting completed
|  | 195 | 39 | 19
New Sprint 8 stories
Tasks | Efforts (in hours) | Story points |  |  | Comments
Create separate application for dealer master
LOGBUS-28140 (Perf Task) | Dev /defects - 40 Testing - 40 |  | 8 |  | 30/01 - FE by Ashish and Backend by Shital 31/01 - FE analysis done. 2 API as sample created 02/02 - Facing issue on Pagination. 06/02 - In progress, creating query for pagination 07/02 - In progress 08/02 - need to connect with Ashish for query. FE in progress 09/02 - code commited for BE. FE in progress 10/02 - FE in progress 13/02 - In progress with FE
LOGBUS-28016 task | Dev - 16 Testing - |  | 5 |  | 31/01 - Akash to pick 01/02 - In progress 02/02 - In progress 06/02 - target today eod 07/02 - Code commited. Need to recommit today with save changes. 08/02 - code commited today, under review. 09/02 - code commited and tested. 1 issue found. Scripting to pick. 10/02 - Scripting in progress. 13/02 - Scripting in progress 15/02 - Scripting completed. 1 issue to be resolved.
Shared components for STOX | Dev /defects - 24 Testing - 8 |  | 5 | 5 | 31/01 - R&D work. Priyanka to pick 06/02 - Not started yet. 07/02 - Started 09/02 - In progress 14/02 - done with analysis and created ticket for that.
LOGBUS-28352 |  |  |  |  | Assigned to Akash 10/02 - In progress 13/02 - Code commited. Issue raised which is in progress 15/02 - Issue resolved.
LOGBUS-28353 |  |  |  |  | Gupta working on Order overview stories 13/02 - 15 STORIES created 14/02 - 4 more stories created, queries in progress
Front end unit testing for STOX settings |  |  |  |  | To pick next week
STOX settings UAM
Xcentry components |  |  |  |  | Not on priority
0
AM Tasks
AdminLAN setup |  |  |  |  | Completed
Test case execution |  |  |  |  | In progress
Backend setup Old app |  |  |  |  | Completed
Frontend setup Old app |  |  |  |  | Completed
New app - Backend setup |  |  |  |  | Completed
New app - Front end setup |  |  |  |  | Completed
Production access |  |  |  |  | Completed

## Sprint 9
Sprint 8 carry over tasks | Efforts (in hours) | Total (in hours) | SP original | Actual SP work | Comments
Defect LOGBUS-27380 | Dev/defects - 18 Testing - |  |  |  | 25/01 - previous issue resolved. Updated the defect with further issues 31/01 - Priyanka to update the current defect with comment for closing the ticket and open new ticket for remaining work 03/02 - trying few more scenarios 06/02 - Few cases need to discuss with Robert 08/02 - Need some expertie on NGXs 21/02 - working with Mangesh and estimate it by today eod 27/02 -Piyush got the solution to implement today EOD. Tommarow morning commit the code after review. 28/02 - Use cases to be covered based on Priyanka's inputs. planning to close by today eod. 03/03 - Need more time to cover all the tabs. 1 or 2 days more. 06/03 - today eod to commit code for all tabs 07/03 - Testing in progress. Patil working and shared observations 08/03 - Testing in progress post fixes.
LOGBUS-28200 client validations | Dev - 8 Testing - 15 | 23 | 8 | 3 | 25/01 - Sheet 1 validations - facing issues. Started with sheet 2 31/01 - Sheet 1 validations are completed for FE. Sheet 2 are code completed and unit testing in progress 01/02 - sheet 2 in progress 02/02 - Sheet 2 reading still in progress 03/02 - Sheet 2 in progress 06/02 - 20% coding pending 23/02 - integration in progress/ 24/02 - Integration completed. Testing in progress, trying to fix some issues 27/02 - Poonam to connect with Piyush and fix the observation(2 issues). 28/02 - one issue is pending to fix 02/03 - Fix is still pending. Someone needs to pick this to close today eod. 03/03 - Testing in progress 06/03 - UI testing in progress. 07/03 - Observations shared, shital working on it. 08/03 - Localization completed, fixes for defects is in progress
LOGBUS-28203 server validations | Dev - 24 Testing - 15 | 39 | 5 | 5 | 31/01 - BE started 01/02 - in progress 06/02 - In Progress 07/02 - In progress 08/02 - working on save button 20/02 - working on one of the API. 21/02 - First API in progress 22/02 - in progress 23/02 - Code commited without one validation 24/02 - validations completed 27/02 - client -server validation integeration tested . for 10 invalid records time takes 2-3 mins,. Next step for valid 10 records. Based on client side US progress ,Testing team can test the US tommorrow 28/02 - Testing can be started once poonam fix the UI issue 06/03 - Testing in progress
LOGBUS-27920 | Dev - 12 Testing - 12 | 24 | 8 | 2 | 31/01 - Code completed, peer testing in progress. 01/02 - code review done, code commit in progress 02/02 - code commit pending, faced some issues 03/02 - Bug found this code not commited. 06/02 - Still in progress 07/02 - 3 APIs to be checked, working on defect 08/02 - in progress(defect logbus-28392). 1 day ETA 09/02 - Trying to resolve few issues of null data 10/02 - in progress 16/02 - dependent on defect 28392
Defect LOGBUS-28392 | Dev - 36 Testing - 8 | 44 |  |  | 16/02 - Ashish to check who can take this up with pooja 20/02 - one tab is completed, other 2 are in progress - one with prasad and one with Pooja 21/02 - some issue with existing code.. Need to check with Shubham 22/02 - In progress. 23/02 - two api's testing completed(dealer data, user settings and stox parts) post code fix. 1 API in progress 24/02 - In progress 27/02 on Friday assigned to Pooja. target to commit the code Tommorow morning. 28/02 - 3rd tab issue fixed, unit testing in progress. Target to close today 03/02 - Code merge testing in progress 06/03 - Testing in progress. 2 tabs went well, 3rd tab in progress 07/03 - Comitting code today. Ready for testing. 08/03 - Testing in progress. Observations shared. Fixes in progress
LOGBUS-28140 (Perf Task) | Dev /defects - 24 Testing - 10 | 34 | 8 |  | 10/02 - FE in progress 13/02 - In progress with FE 16/02 - may need changes in BE based on FE analysis (only for 1 tab) 20/02 - today trying to complete the FE 21/02 - Today to complete the 1st api tab 22/02 - working to fix it today 23/02 - in progress 24/02 - In progress 27/02 - ? this was with Priyanka earlier tommarow to check on update 28/02 - working on the solution. 03/02 - On hold as of now | Need to close this task based on latest suggestion from Robert
|  | 164 | 21 | 10
New Sprint 9 stories
Tasks | Efforts (in hours) | Story points |  |  | Comments
LOGBUS-28471 | 24 | 3 |  |  | Prasad 20/02 - Code fixed, testing in progress. Few observations needs to be discussed with Pavel/Ganesh 21/02 - pending with Pavel 22/02 - still pending with Pavel 24/02 - Close the ticket as Pavel has created separate ticket for validations(LOGBUS-28663)
LOGBUS-28536 | 16 | 2 |  |  | Rushi 20/02 - TESTED, scripting in progress, to close today eod 21/02 - Closed
LOGBUS-28407 | 24 | 3 |  |  | Akash 20/02 - in progress 21/02 - Akash to connect with Ashish for button issue 22/02 - In progress 24/02 - Need more analysis 27/02 - today by EOD to complete 28/02 - one case is not working. Need to connect with Priyanka 03/02 - Ganesh to assign someone on this to help akash 03/03 - Priyanka need to fix this issue.
LOGBUS-28599 | 20 | 3 |  |  | Rushi 20/02 - In progress 21/02 - In progress 23/02 - Pavel suggested the approach. Need help in FE 24/02 - Framework change required. Need to check with priyanka 27/02 - merge conflict happening ,Rushikesh need help to commit the code ,Today commit the code. 28/02 - Code commited and available for testing. Patil to pick testing 02/03 - Testing completed
LOGBUS-28626 Docker deployment |  | 13 |  |  | 21/02 - license received. Facing FE issue, need to check with Mangesh. Check with priyanka first. 27/02 Locally application working with docker ,plan is to address UAM gap and cleanup the code tommarow EOD and move it to merge-stox-to-dev branch. Piyush,Tushar to work on code cleanup tommarow. 28/02 - Targeting by tomorrow eod to mege code and deploy on log1danl
LOGBUS-28615 SICOS estimation |  |  |  |  | 21/02 - estimations worked out with team. Mindmaps needs to be created.
ORDER
LOGBUS- 28381 ORDER | 64 | 8 |  |  | 24/02 - assigned to Prasad 03/03 - In progress 06/03 - working on subpanels 07/03 - Target to complete by tomorrow 08/03 - today eod to complete
LOGBUS- 28382 ORDER | 40 | 5 |  |  | 24/02 - assigned to Rushi
LOGBUS- 28383 ORDER | 40 | 5 |  |  | 24/02 - assigned to Pooja
LOGBUS-28574 | 64 | 8 |  |  | 24/02 - assigned to Poonam and started analysis
LOGBUS-28573 | 64 | 8 |  |  | 24/02 - assigned to Shital
LOGBUS-28384 | 16 | 2 |  |  | 24/02 - assigned to Prasad
LOGBUS-28416 | 104 | 13 |  |  | 24/02 - assigned to Ashish
LOGBUS-28592 | 64 | 8 |  |  | 24/02 - assigned to Akash
LOGBUS-28417 | 40 | 5 |  |  | 24/02 - assigned to Tushar 27/02 Go through the recording to understand current architecture and analysis. | need to reallocate
LOGBUS-28418 | 64 | 8 |  |  | 24/02 - assigned to Priyanka
Front end unit testing for STOX settings - E2E structure. |  |  |  |  | To pick next week
STOX settings UAM
Xcentry components |  |  |  |  | Not on priority
Create separate application for dealer master
Check existing code on its breakage/failiure
| 644 | 94
AM Tasks
AdminLAN setup |  |  |  |  | Completed
Test case execution |  |  |  |  | In progress
Backend setup Old app |  |  |  |  | Completed
Frontend setup Old app |  |  |  |  | Completed
New app - Backend setup |  |  |  |  | Completed
New app - Front end setup |  |  |  |  | Completed
Production access |  |  |  |  | Completed

## Sprint 10
Sprint 9 carry over tasks | Efforts (in hours) | Total (in hours) | SP original | Actual SP work | Comments
Defect LOGBUS-27380 | Dev/defects - NA Testing - 2 | 2 | 13 | 1 | 08/03 - Testing in progress post fixes. 09/03 - Testing in progress 10/03 - Total 5 defects raised. Need to fix them. Assigned to Rushi 13/03 - Db issues were there on 10th. Unable to show the defects to Rushi. 14/03 - Piyush to continue on defects. 15/03 - Today to commit the fixes for all 16/03 - Issues fixed. Testing went well. Can close this.
LOGBUS-28200 client validations | Dev/Defects - 8 Testing - 20 | 28 | 8 | 5 | 08/03 - Localization completed, fixes for defects is in progress 09/03 - Testing in progress and few observations still pending to fix 10/03 - Testing and fixes are in parallel 13/03 - Testing and fixes are in parallel 14/03 - Fix provided. Testing also looks fine. One test scenario in progress 15/03 - FE test for one scenario pending
LOGBUS-28203 server validations | Dev - 8 Testing - 20 | 28 | 5 | 5 | 06/03 - Testing in progress 09/03 - Testing in progress and few observations still pending to fix 10/03 - Testing and fixes are in parallel 13/03 - Testing and fixes are in parallel 14/03 - Fix provided. Testing also looks fine. One test scenario in progress 15/03 - FE test for one scenario pending
LOGBUS-27920 | Dev - 12 Testing - 12 | 24 | 8 | 2 | 16/02 - Dependent on defect 28392 09/03 - To be tested post defect fix of 28392 13/03 - Code commit pending. Automation scripting is in progress 16/03 - one tab pending for scripting. Code to merge with stox settings by tomorrow | Settings
Defect LOGBUS-28392 | Dev - 12 Testing - 24 | 36 | 8 | 8 | 08/03 - Testing in progress. Observations shared. Fixes in progress 09/03 - Working on defect 13/03 - Code commit pending. 14/03 - Code commit pending due to Settings branch unavailability 16/03 - one tab pending for scripting. Code to merge with stox settings by tomorrow | Settings
LOGBUS-28407 | Dev- 24 | 3 | 3 | 3 | 03/03 - Priyanka need to fix this issue. 13/03 - In Progress 14/03 - Post merging, need to cross check the issue | Settings
LOGBUS- 28381 ORDER | Dev/defects - 8 Testing - | 64 | 8 | 1 | 08/03 - Today eod to complete 09/03 - Facing error, need support on solution 10/03 - working with Mangesh/Priyanka for the solution(Blocker) 13/03 - Issue resolved, Filters are pending. Will be available for test. 14/03 - Code commited for the panel. Filter css are pending. 15/03 - check boxes pending. today to commit all the changes 16/03 - localization pending. few alignment issue fixed
LOGBUS- 28382 ORDER |  | 40 | 5 |  | 24/02 - assigned to Rushi 15/03 - Today to start on this
LOGBUS- 28383 ORDER |  | 40 | 5 |  | 24/02 - assigned to Pooja 14/03- Started with BE analysis 15/03 - In progress 16/03 - In progress
LOGBUS-28574 ORDER |  | 64 | 8 |  | 24/02 - assigned to Poonam and started analysis 14/03 - Shital working on BE and Poonam on FE
LOGBUS-28573 ORDER | Dev - 32 | 64 | 8 |  | 24/02 - assigned to Shital 14/03 - Shital working on BE and Poonam on FE 15/03 BE analysis completed. FE In progress 16/03 - BE started coding, FE started coding
LOGBUS-28384 ORDER |  | 16 | 2 |  | 24/02 - assigned to Prasad
LOGBUS-28416 ORDER |  | 104 | 13 |  | 24/02 - assigned to Piyush
LOGBUS-28592 ORDER |  | 64 | 8 |  | 24/02 - assigned to Akash 14/03 - BE analysis in progress
LOGBUS-28417 ORDER |  | 40 | 5 |  | 27/02 Go through the recording to understand current architecture and analysis.
LOGBUS-28418 ORDER |  | 64 | 8 |  | 24/02 - assigned to Priyanka
|  | 681 | 115 | 25
New Sprint 10 stories/Tasks
Tasks | Efforts (in hours) | Story points |  |  | Comments
LOGBUS- 28879 Automation script maintenance | 24 | 3
FE code optimization LOGBUS-28936 |  |  |  |  | Priyanka
Country localization LOGBUS-28937 | 16 | 3 |  |  | Priyanka 14/03 - Solution decided. Need testing post optimization
LOGBUS-28842 Localization issue | 20 | 3 |  |  | Akash 14/03 - In progress 16/03 - need BE changes.
LOGBUS-28939 Demo observations to fix - 0/14
Estimations DIMS - 642, 643, 644, 645, 646 |  |  |  |  | 10/03 - Ganesh and Pratik need to work on these 13/03 - Awaiting on the commit dates. Analysis of the requirement to kick off. 14/03 - dims demo setup today 15/03 - Estimation in progress. Tentative Monday 20Mar
SICOS - 636, 638 |  |  |  |  | 14/03 - Need to adjust the dates for dev. Ganesh to check further on this
SICOS - 660, 663
LOGBUS-28419 ORDER | 24 | 3
LOGBUS-28444 ORDER | 24 | 3
LOGBUS-28445 | 64 | 8
LOGBUS-28446 | 40 | 5
LOGBUS-28661 Dealer | 24 | 3 |  |  | Ashish 16/03 - Discussed with Pavel
LOGBUS-28662 Dealer |  |  |  |  | Ashish 16/03 - Discussed with Pavel. Started and 70% complted
236